### Project: Design and Implementation of SmartCAMPOST: An Intelligent Parcel Tracking, Collection, and Delivery System Using QR Code, GPS, and AI

Developer: Nguend Arthur Johann
Duration: 4 months (17 weeks)
Methodology: Hybrid (Merise + UML + Agile)

PHASE 1 – Internship Integration and Setup (01–14 Oct 2025)

| ID | Task | Duration | Start | End | Predecessor | Deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Internship Integration and Setup | 10d | 01-Oct | 14-Oct | — | Internship initiation complete |
| 1.1 | Administrative registration at CAMPOST | 2d | 01-Oct | 02-Oct | — | Registration validated |
| 1.2 | Meeting with CAMPOST supervisor | 1d | 03-Oct | 03-Oct | 1.1 | Internship objectives defined |
| 1.3 | Understanding CAMPOST services & IT system | 5d | 04-Oct | 09-Oct | 1.2 | Environment report |
| 1.4 | Installation of development tools & system setup | 3d | 10-Oct | 14-Oct | 1.3 | Ready working environment |

## PHASE 2 – System Analysis and Design (Merise + UML) (15 Oct – 02 Nov 2025)

| ID | Task | Duration | Start | End | Predecessor | Deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| 2 | Analysis and Design Phase | 15d | 15-Oct | 02-Nov | 1.4 | Validated design and documentation |
| 2.1 | Requirement gathering (users, agents, administrators) | 5d | 15-Oct | 19-Oct | 1.4 | Requirement notes |
| 2.2 | Creation of Conceptual Data Model (CDM / MCD) | 4d | 20-Oct | 23-Oct | 2.1 | Entity-relationship model |
| 2.3 | Creation of Logical Data Model (LDM / MLD) | 4d | 24-Oct | 27-Oct | 2.2 | Database schema |
| 2.4 | Design UML diagrams (Use Case, Class, Sequence, Activity, Deployment) | 4d | 28-Oct | 31-Oct | 2.3 | UML diagrams completed |
| 2.5 | Supervisor validation of Merise + UML phase | 2d | 01-Nov | 02-Nov | 2.4 | Design approved |

## PHASE 3 – Agile Development and Integration (03 Nov 2025 – 05 Jan 2026)

Each sprint = 2 weeks of iterative work.

| ID | Task | Duration | Start | End | Predecessor | Deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| 3 | Agile Development Phase | 45d | 03-Nov | 05-Jan | 2.5 | Working SmartCAMPOST platform |
| Sprint 1 – Database Setup & Authentication (03–16 Nov) |  |  |  |  |  |  |
| 3.1 | Initialize backend and database | 3d | 03-Nov | 05-Nov | 2.5 | Database ready |
| 3.2 | Develop authentication (login, OTP, user roles) | 5d | 06-Nov | 11-Nov | 3.1 | Auth module completed |
| 3.3 | Test and integrate login system | 2d | 12-Nov | 13-Nov | 3.2 | Secure login verified |
| 3.4 | Sprint 1 Review | 1d | 14-Nov | 14-Nov | 3.3 | Sprint validated |
| Sprint 2 – Parcel Registration & Tracking (17–30 Nov) |  |  |  |  |  |  |
| 3.5 | Develop parcel registration form (QR generation) | 4d | 17-Nov | 20-Nov | 3.4 | Registration module done |
| 3.6 | Implement tracking and SMS notification | 5d | 21-Nov | 26-Nov | 3.5 | Tracking system operational |
| 3.7 | Test & review | 2d | 27-Nov | 28-Nov | 3.6 | Sprint approved |
| Sprint 3 – Agent App & Payment System (01–14 Dec) |  |  |  |  |  |  |
| 3.8 | Develop agent interface (QR scan, validation) | 4d | 01-Dec | 04-Dec | 3.7 | Agent interface functional |
| 3.9 | Integrate digital payments (Orange, MTN, CAMPOST Money) | 4d | 05-Dec | 10-Dec | 3.8 | Payments integrated |
| 3.10 | Sprint review | 2d | 11-Dec | 12-Dec | 3.9 | Payment tested |
| Sprint 4 – Admin Dashboard & AI (15–28 Dec) |  |  |  |  |  |  |
| 3.11 | Develop admin dashboard (React web) | 5d | 15-Dec | 19-Dec | 3.10 | Admin dashboard ready |
| 3.12 | Integrate AI module (delivery prediction) | 4d | 20-Dec | 23-Dec | 3.11 | AI feature implemented |
| 3.13 | Test and bug fixing | 3d | 24-Dec | 26-Dec | 3.12 | Stable version |
| Sprint 5 – Integration & Optimization (29 Dec – 05 Jan) |  |  |  |  |  |  |
| 3.14 | Merge all components (client, agent, admin) | 3d | 29-Dec | 31-Dec | 3.13 | Unified build |
| 3.15 | Full system optimization and UI polishing | 3d | 02-Jan | 05-Jan | 3.14 | Optimized SmartCAMPOST system |

## PHASE 4 – System Testing and Validation (06–20 Jan 2026)

| ID | Task | Duration | Start | End | Predecessor | Deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| 4 | Testing & Validation | 10d | 06-Jan | 20-Jan | 3.15 | Validated platform |
| 4.1 | Functional and performance testing | 5d | 06-Jan | 10-Jan | 3.15 | Test report |
| 4.2 | Supervisor validation with CAMPOST | 3d | 11-Jan | 13-Jan | 4.1 | Approval letter |
| 4.3 | Implement feedback corrections | 4d | 14-Jan | 17-Jan | 4.2 | Improved version |
| 4.4 | Final validation | 3d | 18-Jan | 20-Jan | 4.3 | System ready for deployment |

## PHASE 5 – Documentation, Internship Report, and Defense (21–31 Jan 2026)

| ID | Task | Duration | Start | End | Predecessor | Deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| 5 | Documentation & Reporting | 9d | 21-Jan | 31-Jan | 4.4 | Final report and presentation |
| 5.1 | Write technical and user documentation | 4d | 21-Jan | 24-Jan | 4.4 | Documentation ready |
| 5.2 | Write internship report (ICT University format) | 4d | 25-Jan | 28-Jan | 5.1 | Report draft completed |
| 5.3 | Prepare and rehearse defense presentation | 2d | 30-Jan | 31-Jan | 5.2 | Presentation ready |

## KEY MILESTONES

| Milestone | Date | Dependency |
| --- | --- | --- |
| Internship setup completed | 14-Oct | 1.4 |
| Analysis & Design validated | 02-Nov | 2.5 |
| Sprint 1 completed | 14-Nov | 3.4 |
| Sprint 2 completed | 28-Nov | 3.7 |
| Sprint 3 completed | 12-Dec | 3.10 |
| Sprint 4 completed | 26-Dec | 3.13 |
| System integrated and optimized | 05-Jan | 3.15 |
| System validated by CAMPOST | 20-Jan | 4.4 |
| Report and presentation completed | 31-Jan | 5.3 |